## Read me
Content migration map template
Purpose | Use this sheet to decide where every old URL goes when the new site launches. Each row links back to the content inventory through the Inventory ID, so the two sheets stay in step. Keep it as a working document until launch; an Unresolved row blocks launch until someone decides it.
Tabs | Example: a filled-in migration map. Blank: the same columns and dropdowns with 50 empty rows, ready to use.
Column | What to put in it
Old URL | The current URL.
Old title | The page title on the current site.
Inventory ID | The ID from the content inventory sheet, for example INV-001.
Disposition | The action from the inventory: Keep, Revise, Merge, Remove, To create or Unresolved.
New node | The node ID in the new structure. Write None when the content is retired.
New URL | The replacement URL. Write None (retired) when there is no relevant replacement, or Not decided when the row is Unresolved.
Redirect | Permanent, None or Pending.
Content action | What happens to the content: Move, Rewrite, Merge, Retire or Create.
Owner | The team or role responsible for the move.
Status | Not started, In progress, Agreed, Done or Open.
Notes | Anything the next person needs, including an existing redirect on the old URL.
Rules | Every old URL either has its own row or falls under a pattern rule.
Never leave New URL blank. Give a destination, write None (retired) for a retired URL, or write Not decided and mark the row Unresolved.
Redirect only when there is a relevant replacement. Otherwise retire the URL according to the site's policy.
Avoid redirect chains. If an old URL already redirects somewhere, record that in Notes and point it straight at the final destination.
On large sites, one rule can cover many URLs (for example, a whole folder). Record pattern rules in their own rows.
Licence and attribution | Template by UXbeam · https://www.uxbeam.com/information-architecture/deliverables/ · Licensed CC BY 4.0 (https://creativecommons.org/licenses/by/4.0/). Example data is illustrative: a fictional library website, not a real project.

## Example
Old URL | Old title | Inventory ID | Disposition | New node | New URL | Redirect | Content action | Owner | Status | Notes
https://library.example.org/visit/hours | Opening hours | INV-001 | Merge | N-2.1 | https://library.example.org/visit/hours-and-locations | Permanent | Merge | Branch services | Done | None
https://library.example.org/about/hours-and-locations | Hours and locations | INV-002 | Merge | N-2.1 | https://library.example.org/visit/hours-and-locations | Permanent | Merge | Communications | Done | Summer hours removed
https://library.example.org/kids/storytime | Storytime | INV-003 | Revise | N-3.2 | https://library.example.org/events/storytime | Permanent | Rewrite | Youth services | In progress | Dates move to event entries
https://library.example.org/news/2019-renovation | Renovation update 2019 | INV-004 | Remove | None | None (retired) | None | Retire | Communications | Agreed | No relevant replacement; retired per site policy
https://library.example.org/services/printing | Printing and scanning | INV-005 | Revise | N-2.4 | https://library.example.org/visit/printing-and-scanning | Permanent | Rewrite | IT | Not started | None
https://library.example.org/ebooks-help | E-books help | INV-006 | Unresolved | Not decided | Not decided | Pending | Not decided | Digital services | Open | Blocked on decision D-03
Note on A1: The current URL. Illustrative data: a fictional library website. Not from a real project.
Note on B1: The page title on the current site.
Note on C1: The ID from the content inventory sheet, for example INV-001.
Note on D1: The action from the inventory: Keep, Revise, Merge, Remove, To create or Unresolved.
Note on E1: The node ID in the new structure. Write None when the content is retired.
Note on F1: The replacement URL. Write None (retired) when there is no relevant replacement, or Not decided when the row is Unresolved.
Note on G1: Permanent, None or Pending.
Note on H1: What happens to the content: Move, Rewrite, Merge, Retire or Create.
Note on I1: The team or role responsible for the move.
Note on J1: Not started, In progress, Agreed, Done or Open.
Note on K1: Anything the next person needs, including an existing redirect on the old URL.

## Blank
Old URL | Old title | Inventory ID | Disposition | New node | New URL | Redirect | Content action | Owner | Status | Notes
Note on A1: The current URL.
Note on B1: The page title on the current site.
Note on C1: The ID from the content inventory sheet, for example INV-001.
Note on D1: The action from the inventory: Keep, Revise, Merge, Remove, To create or Unresolved.
Note on E1: The node ID in the new structure. Write None when the content is retired.
Note on F1: The replacement URL. Write None (retired) when there is no relevant replacement, or Not decided when the row is Unresolved.
Note on G1: Permanent, None or Pending.
Note on H1: What happens to the content: Move, Rewrite, Merge, Retire or Create.
Note on I1: The team or role responsible for the move.
Note on J1: Not started, In progress, Agreed, Done or Open.
Note on K1: Anything the next person needs, including an existing redirect on the old URL.